Client Project Proposal & Sprint 1 Plan

# Part A — Project Proposal Summary

## Project Details

Project name: NBN-UX Design Practices Using AI

Client / organization: NBN (National Broadband Network)

Prepared by: Team 22

Date of client discussion: 07/08/2026

## Team & Roles

| Role | Assigned to | Notes |
| --- | --- | --- |
| Project Manager | Hami Faizal | Coordination, communication, research |
| User Experience | Sophie Dorland | User research and problem definition |
| Business Analyst | Helbert Pemba | Research and requirements |
| Developer | Alex Davidson | Research and concept exploration |
| Developer | darcy burke | Research and concept exploration |

## Problem Statement

NBN wants to improve how its teams use and adopt AI in their day-to-day work, particularly across UX, business analysis and other non-technical parts of the software development lifecycle. A key issue identified during the previous NBN workshop was that current AI tools do not support team collaboration well

## Target Users

NBN employees involved in the software development lifecycle who use or could benefit from AI-assisted workflows

## Proposed Solution

Design and develop a prototype that demonstrates how AI could better support collaborative work across NBN teams and improve the way employees use AI within their existing workflows.

## Scope Boundaries

In scope this term:

- Researching and defining relevant AI-assisted UX and collaborative workflow use cases for NBN.

- Designing and prototyping a solution that improves how NBN employees use AI in their work.

- Building an MVP that demonstrates the project's primary use case end-to-end.

- Conducting usability testing to determine what works and does not work for users.

- Refining the MVP based on testing and project findings.

- Producing a solution that is sufficiently researched, designed and developed to present back to NBN.

Out of scope this term:

- Creating or training a new AI/large language model- the project will use existing AI models or services where required.

- Delivering a fully production-ready enterprise system for deployment across NBN.

- Replacing NBN's existing software development or UX processes in their entirety.

- Full integration with NBN's internal production systems unless access and requirements are later provided and agreed.

## 3-Sprint Roadmap

Sprint 1 — Design & Bootstrap: Define priority use cases, solution direction, and complete the initial prototype/design.

Sprint 2 — Raw MVP: Build the core AI-assisted workflow end-to-end as a functional MVP.

Sprint 3 — Refine MVP: Usability test, refine and polish the MVP based on user feedback.

## Success Criteria

A well-researched, well-designed and functional MVP that improves how NBN employees use AI in their work, supported by usability testing and the insights gained about what does and does not work for users. The final outcome should also be of a quality that can be confidently presented to NBN.

## Assumptions & Constraints

- Alessio is acting as a proxy for NBN; direct involvement from NBN staff during the project may be limited primarily to the final presentation, with a possible intermediate session if available.

- Leon will provide further direction on UX-specific scope and requirements.

- The exact solution and priority use cases have not yet been confirmed and will be defined during Sprint 1.

- A multi-user AI system is a possible solution direction, not a fixed client requirement.

- NBN's exact technical, security, privacy and AI-governance requirements were not confirmed during this meeting.

- The specific AI model is not considered the primary technical challenge; existing models such as Claude or other suitable LLMs may be used.

- Any use of paid infrastructure, storage, APIs or AI services will depend on available university/team resources and agreed tooling.

- Both RMIT teams are expected to operate independently and develop different or complementary approaches rather than delivering the same solution.

# Part B — Sprint 1 Plan (Weeks 1–3)

## Week 1

Task 1.1 — Review NBN workshop and client material [PBI 1] Owner; Hami Faizal — PM; Track; Design / Product. Week; 1; Hours; 1.5. Description: Review the supplied NBN workshop material and initial client notes to establish the team’s shared starting context before new solution ideas are formed. Deliverable: Shared notes summarising existing findings, known pain points, assumptions and items requiring clarification. Acceptance criteria: ✓ All supplied NBN/client material reviewed ✓ Key findings, pain points and assumptions captured ✓ Notes added to the shared research document

Task 1.2 — Identify priority assumptions and research gaps [PBI 3] Owner; Hami Faizal — PM; Track; Design / Product. Week; 1; Hours; 1.5. Description: Compare the existing NBN/client material with early team research and turn important uncertainties into explicit questions that can be validated through interviews. Deliverable: Prioritised list of research gaps and validation questions. Acceptance criteria: ✓ User and workflow assumptions are listed ✓ High-impact uncertainties are converted into research questions ✓ Questions are marked for supervisor or NBN employee validation

Task 1.3 — Begin NBN participant recruitment [PBI 6] Owner; Hami Faizal — PM; Track; Design / Product. Week; 1; Hours; 1.0. Description: Identify a suitable NBN participant profile, request introductions where appropriate and begin outreach so an interview can be secured for Week 2. Deliverable: Active outreach and, where possible, a confirmed NBN interview booking. Acceptance criteria: ✓ Suitable participant profile identified ✓ At least one recruitment pathway/contact actioned ✓ Interview purpose, expected duration and next steps communicated

Task 1.4 — Research AI adoption in non-technical workplace activities [PBI 2] Owner; Helbert Pemba — BA; Track; Design / Product. Week; 1; Hours; 2.5. Description: Research organisational AI adoption and challenges in business analysis, collaborative work and other non-technical activities, focusing on user and workflow problems rather than implementation technologies. Deliverable: Source-backed research summary for the shared research document. Acceptance criteria: ✓ Credible sources recorded ✓ Key adoption/workplace challenges summarised ✓ Findings are linked to questions relevant to the NBN project

Task 1.5 — Create a research-question and evidence matrix [PBI 3] Owner; Helbert Pemba — BA; Track; Design / Product. Week; 1; Hours; 1.5. Description: Organise current assumptions, supporting evidence, contradictory evidence and unanswered questions in a structure that can guide the Week 1 interviews and later synthesis. Deliverable: Research matrix showing assumptions, evidence and questions requiring validation. Acceptance criteria: ✓ Assumptions and gaps are clearly separated ✓ Evidence is traceable to its source ✓ Priority validation questions are easy for the team to identify

Task 1.6 — Research collaborative AI UX and multi-user interaction challenges [PBI 2] Owner; Sophie Dorland — UX; Track; Design / Product. Week; 1; Hours; 1.5. Description: Investigate UX challenges associated with collaborative AI use, shared context, multi-user interaction and handovers in team-based work. Deliverable: UX-focused research findings added to the shared research document. Acceptance criteria: ✓ Relevant collaborative AI UX findings recorded ✓ Sources included for significant findings ✓ Insights remain problem-focused rather than solution-led

Task 1.7 — Prepare interview guide and lead supervisor interview [PBI 4 / PBI 5] Owner; Sophie Dorland — UX; Track; Design / Product. Week; 1; Hours; 2.5. Description: Draft an exploratory discussion guide from the team’s research gaps, review it with the team, then facilitate the supervisor interview and capture initial key insights. Deliverable: Final interview discussion guide plus supervisor interview notes and initial insights. Acceptance criteria: ✓ Guide uses open-ended, non-leading questions ✓ Questions cover workflows, AI use, collaboration, pain points and constraints ✓ Interview notes distinguish participant evidence from team interpretation

Task 1.8 — Research how teams use AI in day-to-day work [PBI 2] Owner; Alexander Davidson — DEV; Track; Design / Product. Week; 1; Hours; 2.5. Description: Research how teams currently incorporate AI into everyday collaborative and non-technical work, with attention to behaviours, workflows and recurring friction points. Deliverable: Research summary covering current team AI-use patterns and workflow issues. Acceptance criteria: ✓ Examples of real or observed AI-supported workflows captured ✓ Pain points and behavioural patterns summarised ✓ Sources recorded and findings added to the shared research document

Task 1.9 — Review NBN material for workflow context and support interview preparation [PBI 1 / PBI 4] Owner; Alexander Davidson — DEV; Track; Design / Product. Week; 1; Hours; 1.5. Description: Review the NBN/client material specifically for workflow, handover and context-sharing details, then contribute targeted probes to the supervisor discussion guide. Deliverable: Workflow observations and additional interview probes shared with the team. Acceptance criteria: ✓ Relevant workflow/context observations extracted ✓ Unclear workflow points converted into interview probes ✓ Contributions incorporated into the shared interview preparation

Task 1.10 — Research shared-context, handover and collaboration pain points [PBI 2] Owner; Darcy Burke — DEV; Track; Design / Product. Week; 1; Hours; 2.5. Description: Research problems that arise when people use separate AI tools or agents across a shared task, especially loss of context, handovers and collaboration overhead. Deliverable: Research findings on shared-context and handover pain points. Acceptance criteria: ✓ Shared-context and handover challenges are documented ✓ Sources recorded for significant claims ✓ Findings identify questions that should be tested in interviews

Task 1.11 — Review collaboration pain points and support participant outreach [PBI 1 / PBI 6] Owner; Darcy Burke — DEV; Track; Design / Product. Week; 1; Hours; 1.5. Description: Review existing NBN/client evidence for collaboration-related pain points and support the team’s effort to identify or contact a suitable NBN interview participant. Deliverable: Collaboration observations plus documented recruitment support/actions. Acceptance criteria: ✓ Existing collaboration pain points extracted from supplied material ✓ Potential participant/contact options shared with the PM ✓ Any outreach support or follow-up actions recorded

## Week 2

Task 2.1 — Coordinate and participate in the NBN employee interview [PBI 6 / PBI 7] Owner; Hami Faizal — PM; Track; Design / Product. Week; 2; Hours; 1.5. Description: Confirm logistics, ensure the participant is briefed appropriately and attend the NBN employee interview to capture project-level questions, constraints and follow-up actions. Deliverable: Completed NBN interview with logistics, follow-ups and project-level observations recorded. Acceptance criteria: ✓ Interview time and attendance confirmed ✓ Participant receives clear purpose and meeting details ✓ Project-level constraints and follow-up actions captured

Task 2.2 — Facilitate problem and concept prioritisation [PBI 10 / PBI 11] Owner; Hami Faizal — PM; Track; Design / Product. Week; 2; Hours; 2.5. Description: Guide the team through evidence-based prioritisation of candidate problem statements and concept directions, ensuring decisions consider user value, evidence, relevance and feasibility. Deliverable: Agreed primary problem area and preferred concept direction with decision rationale. Acceptance criteria: ✓ Candidate problem areas compared using explicit criteria ✓ Preferred problem and concept are agreed as a team ✓ Decision rationale and major assumptions are documented

Task 2.3 — Capture and write up the NBN employee interview [PBI 7] Owner; Helbert Pemba — BA; Track; Design / Product. Week; 2; Hours; 1.5. Description: Act as primary note-taker for the NBN employee interview and convert raw notes into a structured record of behaviours, pain points, needs, constraints and assumptions confirmed or challenged. Deliverable: Structured NBN employee interview notes and key insights. Acceptance criteria: ✓ Concrete examples and participant language are preserved where useful ✓ Confirmed/challenged assumptions are identified ✓ Key insights are added to the shared research document

Task 2.4 — Synthesize evidence and draft prioritised problem statements [PBI 8 / PBI 10] Owner; Helbert Pemba — BA; Track; Design / Product. Week; 2; Hours; 2.5. Description: Combine workshop evidence, secondary research and interview findings into themes, then draft evidence-backed candidate problem statements and support team prioritisation. Deliverable: Synthesis themes plus 2–4 candidate problem statements and supporting evidence. Acceptance criteria: ✓ Recurring themes and pain points are supported by evidence ✓ Problem statements remain solution-agnostic ✓ Selected problem area has documented evidence and rationale

Task 2.5 — Lead the NBN employee interview [PBI 7] Owner; Sophie Dorland — UX; Track; Design / Product. Week; 2; Hours; 1.5. Description: Facilitate the interview using the agreed guide, probe for concrete examples and explore current work practices, AI use, collaboration and context-sharing challenges. Deliverable: Completed interview covering the priority research questions. Acceptance criteria: ✓ Interview remains exploratory and non-leading ✓ Current behaviours and concrete examples are explored ✓ Priority research gaps are addressed where possible

Task 2.6 — Define target users, workflows and candidate use cases [PBI 9 / PBI 11] Owner; Sophie Dorland — UX; Track; Design / Product. Week; 2; Hours; 2.5. Description: Use the synthesis to narrow the target users, map relevant collaborative workflows and generate candidate use cases that directly address the prioritised problem. Deliverable: Evidence-backed user/workflow definition and initial set of candidate use cases. Acceptance criteria: ✓ Target users are narrower than “NBN employees” ✓ Important workflow stages and context-sharing points are mapped ✓ Candidate use cases clearly relate to the selected problem

Task 2.7 — Synthesize AI-use workflow patterns [PBI 8] Owner; Alexander Davidson — DEV; Track; Design / Product. Week; 2; Hours; 1.5. Description: Review the combined evidence for recurring patterns in how teams use AI, where context is lost and where handoffs or collaboration introduce friction. Deliverable: Workflow-pattern summary contributed to the team synthesis. Acceptance criteria: ✓ Patterns are linked to more than one evidence source where possible ✓ Evidence is separated from interpretation ✓ Important implementation-relevant constraints are flagged without prescribing a solution

Task 2.8 — Generate and evaluate concept directions [PBI 11] Owner; Alexander Davidson — DEV; Track; Design / Product. Week; 2; Hours; 2.5. Description: Generate multiple concept directions with the team and assess them for feasibility within the capstone timeframe, alignment with the research and suitability for later usability testing. Deliverable: Developer-informed concept options and feasibility evaluation. Acceptance criteria: ✓ Multiple directions are considered ✓ Feasibility risks and assumptions are identified ✓ Evaluation supports the final concept decision rather than overriding user evidence

Task 2.9 — Affinity-group research evidence and surface contradictions [PBI 8] Owner; Darcy Burke — DEV; Track; Design / Product. Week; 2; Hours; 2.0. Description: Group observations across sources into themes, identify recurring pain points and behaviours, and call out contradictions or perspectives that should not be flattened into a single conclusion. Deliverable: Affinity/synthesis contribution showing themes, contradictions and unanswered questions. Acceptance criteria: ✓ Related observations are grouped into meaningful themes ✓ Contradictory evidence is explicitly retained ✓ Unanswered questions are carried forward for concept assumptions

Task 2.10 — Generate and score solution directions [PBI 11] Owner; Darcy Burke — DEV; Track; Design / Product. Week; 2; Hours; 2.0. Description: Generate alternative solution directions and help compare shortlisted concepts against user value, research alignment, feasibility and usability-testing suitability. Deliverable: Alternative concepts plus documented comparison scores/notes. Acceptance criteria: ✓ At least two distinct directions are explored ✓ Concepts are compared using agreed criteria ✓ Major risks and assumptions are recorded for the preferred direction

## Week 3

Task 3.1 — Define Sprint 2 scope and facilitate stakeholder concept review [PBI 12 / PBI 13] Owner; Hami Faizal — PM; Track; Design / Product. Week; 3; Hours; 2.0. Description: Work with the team to define in-scope/out-of-scope boundaries for the selected concept, prepare the review narrative and facilitate feedback with the supervisor/client where possible. Deliverable: Agreed scope boundaries plus recorded stakeholder feedback and decisions. Acceptance criteria: ✓ Sprint 2 scope and exclusions are explicit ✓ Concept review links the proposal back to research evidence ✓ Feedback, decisions and unresolved questions are recorded

Task 3.2 — Close Sprint 1 and prepare the Sprint 2 backlog [PBI 14] Owner; Hami Faizal — PM; Track; Design / Product. Week; 3; Hours; 2.0. Description: Consolidate the Sprint 1 decision trail and coordinate creation, prioritisation and ownership of the Sprint 2 backlog so the next sprint begins from documented decisions. Deliverable: Accessible Sprint 1 closeout record and prioritised Sprint 2 backlog. Acceptance criteria: ✓ Research → problem → concept decision trail is documented ✓ Sprint 2 PBIs are prioritised and provisionally owned ✓ Remaining assumptions and risks are carried into Sprint 2

Task 3.3 — Define functional and UX requirements for the selected concept [PBI 12] Owner; Helbert Pemba — BA; Track; Design / Product. Week; 3; Hours; 2.0. Description: Translate the selected user scenario and concept into core functional requirements, important UX/non-functional requirements and assumptions that still require testing. Deliverable: Initial requirements set for Sprint 2 planning. Acceptance criteria: ✓ Core functional requirements are clear and testable at a high level ✓ UX/non-functional requirements are included where relevant ✓ Open assumptions are explicitly identified rather than hidden as requirements

Task 3.4 — Integrate feedback and decompose work into Sprint 2 PBIs [PBI 13 / PBI 14] Owner; Helbert Pemba — BA; Track; Design / Product. Week; 3; Hours; 2.0. Description: Convert agreed stakeholder feedback into requirement/scope updates and help break the refined concept into appropriately sized Sprint 2 backlog items. Deliverable: Updated requirements plus decomposed Sprint 2 PBIs. Acceptance criteria: ✓ Only agreed/actionable feedback changes the concept or requirements ✓ Changes and rationale are traceable ✓ Sprint 2 backlog items map back to the refined concept and scope

Task 3.5 — Define the key user scenario and end-to-end user flow [PBI 12] Owner; Sophie Dorland — UX; Track; Design / Product. Week; 3; Hours; 2.0. Description: Define the primary user goal, starting context, major interaction stages and intended end-to-end experience for the selected concept. Deliverable: Documented key user scenario and initial end-to-end user flow. Acceptance criteria: ✓ Primary user, goal and starting context are explicit ✓ Flow covers the core scenario from start to finish ✓ Important context-sharing/handoff points are represented

Task 3.6 — Create and refine the low-fidelity concept [PBI 12 / PBI 13] Owner; Sophie Dorland — UX; Track; Design / Product. Week; 3; Hours; 2.0. Description: Create a low-fidelity representation of the selected concept, use stakeholder/team feedback to identify unclear areas and refine the flow or screens without moving into unnecessary high fidelity. Deliverable: Refined low-fidelity concept ready to guide Sprint 2 implementation. Acceptance criteria: ✓ Low-fi concept represents the core scenario and user flow ✓ Feedback-driven changes are incorporated where justified ✓ Concept remains focused on structure and interaction rather than visual polish

Task 3.7 — Review user flow and requirements for implementation feasibility [PBI 12] Owner; Alexander Davidson — DEV; Track; Design / Product. Week; 3; Hours; 1.5. Description: Review the user flow, scope and requirements to identify implementation constraints, dependencies and assumptions that could affect Sprint 2 delivery. Deliverable: Feasibility review with constraints, dependencies and technical assumptions. Acceptance criteria: ✓ Major implementation constraints are identified ✓ Dependencies and uncertain assumptions are recorded ✓ Feedback is framed as trade-offs rather than premature technology decisions

Task 3.8 — Shape prototype structure and Sprint 2 development tasks [PBI 12 / PBI 14] Owner; Alexander Davidson — DEV; Track; Design / Product. Week; 3; Hours; 2.5. Description: Support the low-fi concept with developer input on interaction structure, then translate the refined concept into development-oriented Sprint 2 tasks and rough estimates. Deliverable: Developer-ready task breakdown aligned to the refined concept. Acceptance criteria: ✓ Development tasks map to the agreed user flow and requirements ✓ Tasks respect Sprint 2 scope boundaries ✓ Dependencies, risks and rough effort are documented

Task 3.9 — Review edge cases, handoffs and context-sharing points [PBI 12] Owner; Darcy Burke — DEV; Track; Design / Product. Week; 3; Hours; 1.5. Description: Challenge the initial user flow by checking edge cases, handoffs and places where context could be lost, duplicated or misunderstood across users or AI-supported steps. Deliverable: Edge-case and handoff review with recommended flow clarifications. Acceptance criteria: ✓ Key handoff/context-sharing points are reviewed ✓ Important edge cases or failure points are documented ✓ Recommended changes are tied back to the target workflow/problem

Task 3.10 — Iterate low-fi details and support Sprint 2 risk/effort planning [PBI 13 / PBI 14] Owner; Darcy Burke — DEV; Track; Design / Product. Week; 3; Hours; 2.5. Description: Support refinement of the low-fidelity concept and help identify usability/technical risks, testing assumptions and rough effort considerations for the Sprint 2 backlog. Deliverable: Low-fi refinement contribution plus risk/assumption and effort notes for Sprint 2. Acceptance criteria: ✓ Refinement addresses identified workflow or usability issues ✓ Risks and testable assumptions are recorded ✓ Effort input supports backlog prioritisation without overcommitting to a build approach

✓ Problem and target users documented

✓ Candidate main feature for Sprint 2 identified

✓ Shared with client for confirmation